Trello Project Setup Checklist

Job #25-007-WIU Sallee Hall

Left Column (Project/Contract/Materials Details)

Project Name: WIU – Sallee Hall EOC Renovation – Phase 1

Job #: 25-007-WIU

General Contractor: CORE Construction Services of Illinois, Inc.

GC Project #: 25-04-058

GC Address:601 SW Water Street
Peoria, Illinois 61602

Project Location:University Circle
Macomb, Illinois 61455

Owner: The Board of Trustees of Western Illinois University

Contract Amount: $8,900.00

Scope: Signage (Materials Only - FOB Jobsite)

- Interior Room Signage

- Halo Lit Logo Signage

- All fasteners, hardware, templates

- 15-Year Warranty on Dimensional Letters

Tax Exempt?: Yes (Governmental Agency)

COI Holder:CORE Construction Services of Illinois, Inc.
601 SW Water Street
Peoria, Illinois 61602

COI Submission: Upload via link from compliancechagisb.com (JONES)

Middle Column (To Do - Moon River)

[ ] Submit COI

- Upload to compliancechagisb.com

- Project Name: WIU – Sallee Hall EOC Renovation – Phase 1

- CORE Project Number: 25-04-058

- CGL Limits: $1M/$2M

- Auto Limits: $1M

- Workers Comp: Statutory + $1M/$1M/$1M

- Add Waiver of Subrogation

[ ] Create Procore Account

- Go to www.procore.com

- Request invitation from CORE Project Manager for Project #25-04-058

[ ] Prepare Submittals

- Shop drawings for Dimensional Letter Signage (Spec 101419)

- Shop drawings for Room ID Signage (Spec 101423.16)

- Product data for all materials

- Samples for Architect approval

[ ] Review Drawings

- Thoroughly review Drawing A12.02 (Signage Schedule & Details - Add #2) for full scope.

[ ] Coordinate with Installer

- Identify installation subcontractor

- Provide all necessary mounting templates and hardware

[ ] Prepare 15-Year Warranty

- Draft special warranty document for Dimensional Letter Signage

[ ] Coordinate Delivery

- Schedule delivery with CORE and WIU prior to shipment

- All materials are FOB Jobsite

[ ] Track Payments

- Invoice monthly at 90% of materials delivered

- Note: Payment not due until 7 days after CORE is paid by Owner

- 10% retainage held until final payment

- Submit unconditional lien waivers with each pay app